## Sheet1
Book Launch Timeline
Instructions: Enter your launch date in cell C27 and you'll automatically generate the scheduled dates for each activity. These milestones have already been set for you. However, you will probably want to change the milestone days in each section to fit your specific timeline. If so, then change the number in the 'Days to Book Launch' (Column B) and the deadline date will be updated. You can also insert additional tasks and copy the formulas from existing cells.
Pre - Launch | Days to Book Launch | Deadline
12 Weeks Before Launch
Launch Team: |  | 2020-09-09
Make a list of people you want on your launch team | 84 | 2020-06-17
Prepare materials for them | 84 | 2020-06-17
Contact them | 84 | 2020-06-17
Order advanced reader copies from Sue Kennedy Publishing | 84 | 2020-06-17
Media Kit: |  | 2020-09-09
Get a high-res photo of you | 84 | 2020-06-17
Create other visuals that you can use in promotion | 84 | 2020-06-17
Check your media kit is complete | 84 | 2020-06-17
Endorsements: |  | 2020-09-09
Send a pdf of your manuscript to industry leaders to get more endorsements | 84 | 2020-06-17
Add them to your manuscript | 84 | 2020-06-17
Finalise your book content | 84 | 2020-06-17
10 Weeks Before Launch | 70 | 2020-07-01
Web Presence: |  | 2020-09-09
Choose and buy your domain name and hosting | 70 | 2020-07-01
Set up a specific web page or book blog | 70 | 2020-07-01
Create your ‘Coming Soon’ and ‘Launching Now’ landing pages | 70 | 2020-07-01
Write your email sequence for subscribers to your new opt-in | 70 | 2020-07-01
Complete your Author Academy Bookstore Author page | 70 | 2020-07-01
Launch Team: |  | 2020-09-09
Finalise your list and notify people that they’re on the team | 70 | 2020-07-01
Send them their advanced reader copy (physical book if possible or pdf) | 70 | 2020-07-01
Set up an email list for this group and have your team opt-in | 70 | 2020-07-01
Create a private Facebook group and sign them up to it | 70 | 2020-07-01
Organise a start event such as a Facebook livestream to welcome and take questions | 70 | 2020-07-01
6-8 Weeks Before Launch | 56 | 2020-07-15
Promotional Activities: |  | 2020-09-09
Check you’re set up on the social media platforms you want to use | 56 | 2020-07-15
Start posting about your book | 56 | 2020-07-15
Contact journalists and influencers | 56 | 2020-07-15
Set up interviews | 56 | 2020-07-15
Create and post photos of you, your book and other visuals | 56 | 2020-07-15
3-4 Weeks Before Launch | 28 | 2020-08-12
Plan Book Tours (physical and virtual): |  | 2020-09-09
Contact local book shops to arrange book signings | 28 | 2020-08-12
Plan Launch Party (physical and/or virtual): |  | 2020-09-09
Book the physical venue and organize catering | 28 | 2020-08-12
Send invitations to VIP guests | 28 | 2020-08-12
Press Release: |  | 2020-09-09
Prepare your press release | 28 | 2020-08-12
Prepare a list of journalists and media contacts to send it to | 28 | 2020-08-12
1 to 2 Weeks Before Launch | 14 | 2020-08-26
Review: Go over your plan again and make sure you’ve covered all tasks | 14 | 2020-08-26
Test: Check your processes and tech works smoothly | 14 | 2020-08-26
Launch Day |  | 2020-09-09
Formulas:
Deadline = C58-[Days to Book Launch]